# SYDNEY FESTIVAL
DISABILITY ACTION PLAN 
2014 – 2015
(JUNE 2014)

SYDNEY FESTIVAL

- DISABILITY ACTION PLAN 2014 – 2015

TABLE OF CONTENTS

- Introduction									2

  - Sydney Festival overview			 			2

  - Mission									2

- DAP principles								3

- DDA responsibilities & Legislation						3

- Development of Sydney Festival DAP					4

- Key focus areas								5

- Monitoring, evaluation and review						6

- Sydney Festival Disability Action Plan					7-17

1	INTRODUCTION

The Sydney Festival Disability Action Plan has been developed in response to our ongoing commitment to the provision of dignified access to our yearly program and communications systems. It also demonstrates Sydney Festival’s commitment to compliance with the intent of the Commonwealth Disability Discrimination Act 1992 (DDA).

Sydney Festival has consulted with Accessible Arts, key Sydney Festival staff, peak disability organisations and significant individuals, audiences and potential audiences in the preparation of this Plan. The Plan will be lodged with the Human Rights and Equal Opportunity Commission (HREOC) and will be distributed to interested parties upon request. The Plan will also be available on the Sydney Festival website at www.sydneyfestival.org.au in both PDF and Word formats.

1.1	Sydney Festival overview

Sydney Festival was created by City of Sydney, the Committee for Sydney and the State Government in 1976. Motivated by a desire to enliven the CBD during the quiet month of January, they aimed to both draw in the local population and to attract visitors for a celebration of culture and entertainment set amidst the natural beauty of Sydney. The Festival of Sydney was to be a celebration – to unify and inspire.

Some key planks in Sydney Festival’s foundations put down in those early years have persisted as defining characteristics, such as the emphasis on free events and the creation of Festival precincts which illustrate the inclusive approach to programming.

Over the years and under the influence of seven directors, Sydney Festival has evolved, much as Sydney itself has been changing. As the arts events available to audiences throughout the year have become more plentiful, more sophisticated and more illustrative of national and international trends and themes, so too has the Sydney Festival program.

  - Sydney Festival Mission

To present an arts and entertainment program that celebrates summer across Sydney, enriching the lives of both the city’s residents and visitors.

# 2.	DAP PRINCIPLES

The key guiding principle at issue is that all events should be accessible to the whole population. This principle is not predicated on legislative or regulatory requirements, but rather on the recognition that the Sydney Festival is for all in Sydney, regardless of accessibility needs. In line with this thinking and by way of example, if a space is easily accessible by patrons who use a wheelchair, then it follows that this space will also be easily accessible for all patrons including people with limited mobility; people making deliveries and families with prams.

For the purpose of this plan, it is best to define “disability” in the broadest sense, including physical, sensory, intellectual and psychological disabilities. Further, it is important that the barriers preventing those with disability from participating in Sydney Festival are identified and remedied.

The term ‘barrier’ refers to an obstacle that may be encountered which restricts a person with disability from fully participating in community life. Barriers can be physical, attitudinal and communicational, and can often be easily removed or modified so that the level of access is increased.

The term ‘access’, therefore refers to the removal of barriers and is generally used to describe outcomes. For example, an accessible toilet is one which is modified in a way in which all members of the community can use the facility regardless of their level of ability or disability.

As a result of implementing a DAP, Sydney Festival can maximise its reach, as more people are able to engage with the Festival in more ways.

# 3.	DDA RESPONSIBILITIES & LEGISLATION

The Commonwealth Disability Discrimination Act 1992 (DDA) makes it unlawful to discriminate against someone on the basis of their disability or a disability of any associates of that person, aims to promote equal opportunity and access for people with disabilities, and to educate the community about the rights of people with disability.

The definition of "disability" in the DDA includes:

- Physical

- Intellectual

- Psychiatric

- Sensory

- Neurological, and

- Learning disabilities, as well as

- Physical disfigurement, and

- The presence in the body of disease-causing organisms.

There is no legal obligation for a person to disclose their disability, unless it is likely to affect their ability to meet the inherent requirements of a job.

Australia was one of the first signatories of the United Nations Convention of the Rights of Persons with Disabilities (CRPD); an international legal document recognising that every person with disability has a right to enjoy the human rights that all people have. In particular, article 30 of the Convention refers to the human right of people with disability to access and participate in cultural life, recreation, leisure and sport;

(a) Enjoy access to cultural materials in accessible formats; 

(b) Enjoy access to television programmes, films, theatre and other cultural activities, in accessible formats; 

(c) Enjoy access to places for cultural performances or services, such as theatres, museums, cinemas, libraries and tourism services, and, as far as possible, enjoy access to monuments and sites of national cultural importance.

# 4.	DEVELOPMENT OF THE SYDNEY FESTIVAL DAP

Since the first DAP was written in 2010, many initiatives have been both continued and introduced.  These include;

Access to Sydney Festival services and programs;

- Partnership with Vision Australia to provide Audio Description for select performances.

- Partnership with Go Theatrical for captioning on select performances and online video content.

- Since 2013 the program brochure has been produced and distributed as a braille document, an audio CD and as a Word document in large print format by Vision Australia, and also as MP3 files, an interactive brochure and PDF version, all directly downloadable from the website.

- The brochure and website include an Access section which outlines how to book tickets and gives an explanation of access symbols used in marketing materials. Bookings for people with access needs are made direct with the Festival office by telephone or email.

- Sydney Festival is happy and able to receive phone calls using the ACE Relay service.

- The Festival website adheres to W3C Web Content Accessibility Guidelines for the website and smartphone app.

- All Festival marketing collateral carry access symbols for the relevant events / venues.

- Sydney Festival supports the Companion Card program. Sydney Festival offers tickets at no cost to holders of a Companion Card.

- All Festival controlled outdoor venues have dedicated accessible parking spaces or designated drop off areas and accessible viewing areas for patrons with disability, with clearly signed accessible toilets and a marshal or volunteer assigned to assist patrons with queries.

- Designated wheelchair spaces for ticketed events in venues are sold at the lowest price in the house for that performance.

Staff Training:

- Disability awareness training sessions for cross-departmental, permanent and contract staff members are held twice a year.

- Sydney Festival ensure that the front of house staff of venues where Audio Description is offered have undertaken greeting and guiding training.

# 5. 	KEY FOCUS AREAS

An internal audit of current Sydney Festival practice has been undertaken. Sydney Festival departments, including Marketing, Production, Programming and Corporate Partnerships, were consulted for their input, and a number of DAPs from external organisations have been compared to give a foundation for the Festival’s plan. Additionally, weight has been given to a number of checklists provided by Accessible Arts NSW to cross-reference against current and future Festival practice.

As a result of the audit, a number of key areas to be focused on include:

- Communications

- Human resources

- Venue issues

- Ticketing services

- Programming initiatives

- External stakeholders

These areas cover the breadth of Festival activity in relation to accessibility planning as outlined below:

Communications:

Sydney Festival offers the public clear and easy to obtain information about accessibility at Festival events and venues. The information is to be presented in a variety of ways to maximise accessibility. Further, as part of the development of Sydney Festival’s Digital and Content Strategy, avenues will be explored in the online space to provide content for those Festival patrons who are unable to attend Festival events due to a disability.

Human Resources:

The Festival is non-discriminatory in hiring policy and workplace practice.  It provides training to staff employed, both directly and as contractors, so that staff can manage accessibility issues.

Venue Issues:

Sydney Festival controlled and created venues are designed to be as accessible as possible, and the Festival works with the management of hired venues to ensure the same where possible. Preference will be given to venues which are accessible to people who use wheelchairs. However, if the artistic vision of a project is compromised by not using a particular venue due to its inaccessibility, alternative options will be investigated for patrons who use wheelchairs to access the performance.

Ticketing Services:

The Festival works to ensure that booking procedures are accessible to as much of the community as possible, and that provision is made at venues to cover the needs of patrons with disability.

Programming Initiatives:

Sydney Festival wishes to research and implement best practice to enhance the enjoyment of live performance for patrons with hearing and vision impairments. This includes an understanding of available options as well as technological innovations, with consultation regarding production and performance time selections (taking into consideration any logistics which inhibit the implementation of some initiatives).

External Stakeholders:

Consultation and cooperation with external organisations is carried out to maintain and improve standards.

# Vision

That Sydney Festival is proactive in ensuring that it is broadly accessible to its audiences, staff and artists, and that practices are inclusive and are undertaken to maximise their positive effects on the planning and delivery of the Festival.

# Objectives

Communications:

To communicate access initiatives effectively to people with disability.

Human Resources:

To ensure Sydney Festival maintains a high standard of internal accessibility policy.

To provide access to a knowledge base regarding accessibility issues to Festival staff.

Venue Issues:

To maintain and improve standards of accessibility at Sydney Festival controlled venues to ensure that patrons with disability are not unfairly disadvantaged.

Ticketing Services:

To ensure that access to Festival ticketing is equitable.

Programming Initiatives:

To explore avenues to improve accessibility at Festival performances for physical, sensory, intellectual/ psychological and other disabilities.

External Stakeholders:

To consult and develop relationships with external stakeholders with expertise in accessibility issues, and consult with visiting artistic companies to utilise their existing access initiatives.

6.	MONITORING, EVALUATION AND REVIEW

The Sydney Festival Disability Action Plan 2014 - 2015 is aligned with the Sydney Festival Business Plan.

The objectives and actions listed in this Disability Action Plan 2014-2015 (pages 7-17) are achievable and there are monitoring and evaluation mechanisms in place. By focussing on the evaluation of the previous Festival, departments will ensure that access will be improved rather than actions merely being completed.

This plan will be reviewed and updated annually as the planning for each annual program progresses.  A progress report will be submitted to the Executive Director at the completion of each annual review.

# ACTIONS

The following actions have been identified as ways in which accessibility to Sydney Festival may be maximised.

| ACTIONS |  | Monitoring | Evaluation | Responsibility | Timeframes |
| --- | --- | --- | --- | --- | --- |
| - Objective: Communicating access initiatives effectively to people with disability |  |  |  |  |  |
| 1.1 | The addition to the Sydney Festival website of an area designated specifically to accessibility information | A dedicated accessibility information page was again included on the website in 2014 | Continue to prioritise prominence of the link to the dedicated access page in the design brief for the 2015 website | Marketing | Website deadline |
| 1.2 | Sydney Festival website to meet benchmark standards of accessibility, including, but not limited to, audio versions and ensuring its compatibility with screen reading software | Worked with web designer to ensure compliance with W3C standards in 2014. Ensured the smartphone app was screen-reader compatible and provided open captions on all online Festival thinking episodes | Continue to ensure web designer prioritises accessibility and works to W3C standards. Ensure all images on the 2015 website are tagged correctly | Marketing | 2015 Festival Season Launch |
| 1.3 | Marketing collateral (brochure, maps, mini-guides) to be created in alternate formats to assist people with vision impairment including, but not limited to, an interactive brochure, audio CD and MP3 files, braille and large print Word versions of the brochure | Interactive version, PDF, Word document in large print format and MP3 files were all available directly from the SF website in 2014. The audio CD was available via Vision Australia and a braille version was available via SF directly. We also offered a synopsis of any production in the program as a Word document. | Continue to provide the brochure in alternate formats, including a Braille version for 2015 and beyond. Continue to offer a Word doc synopsis of any production in the program. Ensure that Vision Australia produce the CD version by the deadline, and look into using a well-known actor to use the CD as a wider marketing tool | Marketing | 2015 brochure deadline |
| 1.4 | Maintenance and display of accessibility symbols in Festival collateral and website | Accessibility symbols were included on major Festival collateral and on the website in 2014 | Continue to include symbols on all collateral and ensure they are included on all event pages on website | Marketing | 2015 brochure deadline |
| 1.5 | Assist sponsors and other content providers with creating/distributing accessible content and material | Studio online video content was not open captioned. | Continue to encourage Sydney Festival partners to look into captioning any audio material on their websites | Accessibility Coordinator / Marketing / COPA | Pre- 2015 Festival program launch |
| 1.6 | Establish ongoing relationships with peak disability organisations to facilitate the marketing of Sydney Festival accessibility information via their publications and networks, including alternative format media | Both an accessibility press release and an accessibility leaflet were produced and sent to a comprehensive list of NSW disability groups and organisations for the 2014 Festival | Continue ongoing relationships and establish new ones with relevant organisations and individuals | Marketing / Accessibility Coordinator | Ongoing |
| 1.7 | Up to date accessibility information regarding venues, both hired and Sydney Festival controlled, to be entered into the Sydney Festival website, with a specific focus on large scale event venues such as the Domain and Parramatta Opening Party. | Accessibility information for venues was included on the 2014 website from launch date | Ensure that comprehensive access information for each venue is again included on website in 2015 | Marketing / Ticketing / Production | By 2015 website deadline / season launch date |
| 1.8 | Up to date accessibility information regarding venues, both hired and Sydney Festival controlled, to be included in the Sydney Festival brochure and other printed materials, with a specific focus on large scale event venues such as the Domain and Parramatta Opening Party. | This has been done successfully since 2011 | Access information again also to be included on media releases for Sydney Festival controlled venues | Marketing and Ticketing | By 2015 brochure & collateral deadlines |
| 1.9 | Ticketing and booking information provided in multiple formats to allow for different accessibility needs | Brochure is available in different formats, which includes ticket booking information. A braille brochure was again produced for the 2014 Festival. There is a dedicated access ticketing email address and dedicated Ticketing team member (who undertakes Disability Awareness Training). Publicised that we accept NRS phone calls | Continue to provide the ticketing information in different formats (including braille again for 2014 and beyond, depending on funding) and continue to have a dedicated accessible ticketing email address and team member | Marketing and Ticketing | 2015 brochure deadline and website deadline / season launch date |
| 1.10 | Provide a formal way for people with disability who have attended a Sydney Festival event to give feedback | The 2014 access page on website and in brochure invited feedback via an email address and telephone number. Any comments or complaints go to the Ticketing Manager. | Again invite feedback via the access email address and telephone number | Marketing | 2015 brochure and website deadlines |
| 1.11 | Include questions on disability in our audience surveys to ascertain the community’s reaction to our initiatives, give us suggestions about areas for further improvement and help to create awareness generally. | No question regarding accessibility was included in general audience surveys in 2014. No specific access audience survey was conducted. All patrons who booked a ticket for an audio described performance were spoken to after the show for feedback | If possible, questions on SF accessibility to be included on any general research surveys during the 2015 Festival | Marketing | January 2015 |

| ACTIONS |  | Monitoring | Evaluation | Responsibility | Timeframes |
| --- | --- | --- | --- | --- | --- |
| - Objective: Ensuring Sydney Festival maintains a high standard of internal accessibility and that Festival staff are fully trained regarding accessibility issues |  |  |  |  |  |
| 2.1 | Updating training for permanent staff on accessibility issues | Accessible Arts’ Disability Awareness training is undertaken by permanent and contract staff members across departments to encourage a collective approach to access issues within SF | Continue with June and October training sessions for SF staff (to capture any new permanent members of staff plus contract staff). | Accessibility Coordinator | June & October 2014 |
| 2.2 | All event staff, including, but not limited to, volunteers, marshals, security, to receive thorough briefings on access issues relevant to the event | Volunteers were briefed on access issues relevant to the event in 2014. Marshals and security are currently briefed by event coordinators on accessibility issues at events | Continue to include access in volunteer briefings. ECs to double check the accessibility plan for their event sites | Production and Marketing | December 2014 and January 2015 |
| 2.3 | Sydney Festival proactively communicates that it is an equal opportunity employer by stating that in job ads, and where the services of a recruitment agency is appropriate, it includes the utilisation of agencies that provide recruitment services for people with disability. | Clearly stated in the Sydney Festival Work Health and Safety policy (which forms part of staff contracts), staff contractor handbooks and safety manual | All job ads to include a statement to indicate that Sydney Festival is an EEO employer | Financial Controller | Ongoing |
| 2.4 | Maintain accessibility standards for all staff, both within the office and on external sites | Sydney Festival has a fully trained Workplace Health and Safety committee of 4 permanent staff members who ensure accessibility standards are adhered to | Continue to consider accessibility standards in the design of any new office accommodation / external SF sites | WHS committee members | WH&S committee meetings |

| ACTIONS |  | Monitoring | Evaluation | Responsibility | Timeframes |
| --- | --- | --- | --- | --- | --- |
| - Objective: To maintain and improve standards of accessibility at Sydney Festival controlled venues |  |  |  |  |  |
| 3.1 | Prominent and helpful signage providing direction to accessible toilets and services at Sydney Festival controlled events | Signage is provided for the accessible viewing area and accessible toilets, and a marshal is assigned to the accessible viewing area to provide assistance and information | Continue to provide signage and marshals at the accessible viewing areas of Sydney Festival controlled events | Marketing and Production | 2015 Festival signage deadline (early October 2014) |
| 3.2 | Designated accessible viewing / rest areas to be designed into the layouts of Festival controlled venues at large scale outdoor events | All Sydney Festival controlled outdoor events in 2014 again had accessible viewing / rest areas for people with disability | Continue to provide rest/accessible viewing areas at all Sydney Festival controlled large scale outdoor events | Production | 2015 development application deadlines |
| 3.3 | Provision of accessible places to order and consume food/beverages | Accessible areas to order and consume food and beverages were provided in 2014 where possible (Festival Village food and beverage areas were fully physically accessible). This is not always possible where vans and trucks provide the food | Continue to make food/beverage areas accessible where they are designed by the Festival. Where van and truck based food outlets are used, the Catering Manager is to ensure the staff are aware that they should come out to take and give out orders as necessary | Production | 2015 catering plan deadlines (Sep/Oct 2014) |
| 3.4 | Assess and maintain accessibility of information booths and temporary box offices run/built by Sydney Festival | The 2014 information booths and temporary box offices all included a marshal or volunteer who could assist people with disability | Continue to assign marshals/ volunteers to the temporary box offices to assist patrons with information and booking tickets | Production | 2015 development application deadlines |
| 3.5 | Provide a number of bookable accessible parking spaces for Festival events at the Domain and clearly communicate the existence of such areas, booking information and set-down arrangements | A number of accessible parking spaces for Mobility Parking Scheme Permit Holders at the Domain are provided, publicised in the brochure and on the website. When all the parking spaces have been booked, the Domain team communicate accessible set-down arrangements with patrons. A security guard and volunteer are assigned to the accessible parking area | Continue to provide bookable accessible parking spaces and set-down arrangements and ensure this information is clear in all marketing materials regarding the Domain concerts. Continue to assign a security guard and volunteer to the accessible parking area | Production and Marketing | Marketing; 2015 brochure & collateral deadlines. Production; Dec / Jan Domain planning |
| 3.6 | Production team to address accessibility during the design and running of Sydney Festival controlled venues | Accessibility has always been a focus of the design of Sydney Festival controlled venues | Continue to make accessibility a priority during the design of Sydney Festival controlled venues | Production | Venue confirmation deadlines |

| ACTIONS |  | Monitoring | Evaluation | Responsibility | Timeframes |
| --- | --- | --- | --- | --- | --- |
| - Objective: To ensure that access to Festival ticketing services is equitable |  |  |  |  |  |
| 4.1 | Provide information about ticketing for people with disability in all event specific collateral | Contact details for wheelchair ticket bookings and for other access initiatives were included in the brochure and on the website, but not in any other collateral | Continue with ensuring ticket booking information is included in main brochure and on website | Marketing and Ticketing | 2015 brochure and website deadlines |
| 4.2 | For patrons wishing to book multiple events, ensure best customer service by retaining a dedicated member of the Sydney Festival ticketing team as the single point for people requiring specific information related to access, but also ensuring all ticketing team members are trained to fulfil the role. | All ticketing team member had undertaken Disability Awareness training, and one member of the team was dedicated to accessibility ticket bookings, although any member of the ticketing team was able to assist | Ensure that the whole ticketing team undergoes Disability Awareness training for the 2015 Festival, and again make one member the main contact point for access ticket bookings | Accessibility Coordinator / Ticketing and Customer Services Manager | Training to be organised for early October 2014 |
| 4.3 | All booking options made readily available for people with a disability | Dedicated email address and telephone number was promoted in all collateral and website, along with statement that we accept NRS phone calls | Continue to provide email address and telephone options, and provide the contact information to people who attempt to book accessibility tickets online | Ticketing and Customer Services Manager | 2015 brochure and website deadlines |
| 4.4 | Sydney Festival call centre staff trained to provide appropriate information and contacts to facilitate bookings for people with disability through the Festival booking office | Call centre staff were briefed on the procedure for 2014 | Call centre staff should again be briefed to channel patrons with disability through to the Festival booking office | Ticketing and Customer Services Manager | 2015 Call centre staff briefing session (1 week prior to on-sale) |
| 4.5 | Accessibility information is provided to sellers and patrons at all points of sale, including Sydney Festival call centre, other agency call centres, box offices and online ticketing portals. | Accessibility information was provided to all sellers and patrons at all points of sale in 2014 | Ensure accessibility information is again provided at all points of sale in 2015 | Ticketing and Customer Services Manager | Included in briefing notes 1 week prior to on-sale |
| 4.6 | Wheelchair seating spaces held on the ticketing system for Festival controlled venues and sold at the lowest price in the house for that performance. | Wheelchair seating spaces were held on the ticketing system and sold at the lowest price for that performance in 2014 – stated in the brochure and online | Continue the policy of holding wheelchair seating spaces at Festival controlled venues and selling them at the lowest price for that performance | Ticketing and Customer Services Manager | Include in the 2015 event builds |
| 4.7 | Providing a complimentary ticket to companions of people with disability at every Festival event under the Companion Card program. | Promoted in the brochure and on website. | Continue to support the Companion Card program | Ticketing and Customer Services Manager | Ongoing |
| 4.8 | Generally maintain equitable ticket pricing for people with a disability. | In 2014 designated wheelchair spaces were sold at the lowest price in the house for that performance, and holders of a Companion Card are issued tickets at no cost for their companion. Concession card holders are able to obtain a concession price on ticketed events if applicable (subject to availability) | Continue with the concession programs, and ensure to include the concession ticket information in the access page on website and in the event pages and access section of the brochure | Programming, Marketing & Ticketing and Customer Services Manager | By the 2015 website and brochure deadlines and include in the event builds |

| ACTIONS |  | Monitoring | Evaluation | Responsibility | Timeframes |
| --- | --- | --- | --- | --- | --- |
| - Objective: To explore avenues to improve accessibility at Festival performances |  |  |  |  |  |
| 5.1 | Liaise closely with hired venues to maximise accessibility at Sydney Festival events | Accessibility questions were asked of every hired venue used in the 2014 Festival and if necessary, SF investigated alternative ways to ensure productions could be made accessible to patrons who use a wheelchair | Continue relationships with hired venues and evaluate accessibility | Production and Programming | As productions and venues are being confirmed for Sydney Festival 2015 |
| 5.2 | All Sydney Festival venues audited to ascertain available facilities to assist patrons with a sensory disability or who have a mobility impairment | Access review done of Sydney Festival 2014 venues which included hearing loops, lifts, accessible toilets, etc. | Review all 2015 venues for accessibility and to make this information available again on the website | Accessibility Coordinator / Marketing | By 2015 website deadline / season launch date |
| 5.3 | Programming department to include in artist discussions questions regarding whether the artist is amenable to various accessibility initiatives, including surtitling/captioning of performances, Auslan signing of performances, audio description, or the delivery of content as scripts | Companies were not routinely asked accessibility questions for the 2014 Festival but discussions were held with individual companies when an issue was raised | Include in discussions with companies about whether they / the artist are amenable to utilising accessibility initiatives on their production, if a barrier to access is identified during initial inter-departmental discussions | Programming | As productions and venues are being confirmed for Sydney Festival 2015 |
| 5.4 | Assessment on the annual program and implementation of appropriate and feasible options to assist vision and hearing impaired patrons through the use of surtitles, captioning, Auslan, audio descriptions, etc. | Early assessment of the 2014 program enabled the SF team to effectively discuss which productions could be suitable for utilising accessibility initiatives, and to determine any potential barriers to access | All companies of confirmed productions to be asked if they have used surtitling/captioning/audio description/Auslan interpreting previously on the production (if it is not a new production). This information to be included in the programming department meeting notes to facilitate the assessment of confirmed shows for their Auslan interpreting/captioning/audio description suitability | Access Coordinator / Programming and Production | As productions and venues are being confirmed for Sydney Festival 2015, prior to the brochure deadline |
| 5.5 | Research into new technologies and services for delivery to improve accessibility to the program and the cost implications of employing these technologies | Various technologies for Auslan interpreting, Audio Description and captioning were investigated | Production team and Accessibility Coordinator to continue to research new technologies and ways of incorporating these into the annual program | Accessibility Coordinator / Production | Ongoing |
| 5.6 | Identification of funding sources required to implement new accessible services | Specific accessibility funding applied for but not received in 2014 | Philanthropy and Development teams to source funding opportunities from corporate / Government / private sources | Accessibility Coordinator / Development and Philanthropy | Ongoing |
| 5.7 | Alignment with the new Digital Content Strategy to develop new means by which programmed events can be distributed to the public who cannot attend events due to disability | SBS Studio’s Festival TV filmed 16 Festival shows and installations which were shared as mini-episodes online and packaged into 3 ½ hour shows on Foxtel. ABC Classic FM, 702 ABC Sydney and FBi Radio also recorded numerous shows for radio broadcast | Continue to think of new digital ways programmed events can be made accessible, continue to encourage partners to broadcast performances | Accessibility Coordinator / Marketing | Ongoing – throughout planning stages for 2015 Festival |

|  | ACTIONS | Monitoring | Evaluation | Responsibility | Timeframes |
| --- | --- | --- | --- | --- | --- |
| - Objective: To consult and develop relationships with external stakeholders with expertise in accessibility issues |  |  |  |  |  |
| 6.1 | Develop relationship with Accessible Arts | Accessible Arts has been extensively consulted - obtaining their advice, training, assistance with DAP planning, attending AA organised forums and conferences and being a member of their Accessing The Arts Group for arts and cultural institutions | Continue to maintain relationship, SF Marketing Manager to also to forge relationship with the Accessible Arts Marketing and Communications team | Accessibility Coordinator / Marketing | Ongoing |
| 6.2 | Develop relationship with the City of Sydney Inclusion Officer | Ongoing relationship with the City of City Inclusion Officer | Continue good working relationship and consult as necessary | Accessibility Coordinator | Ongoing |
| 6.3 | Consult with relevant disability sector representatives and audiences/patrons with sensory disability regarding how to determine production and performance time selection for providing accessibility services | Ongoing consultation with, among others; - Accessible Arts - Vision Australia - members of the Deaf Community - Deaf Society of NSW - Individuals with disability - Event Access and Inclusion Manager, Event Strategy Branch, DPC - People with Disability Also spoke directly with patrons of audio described performances and tours of the 2014 Festival and invited feedback | Continue to develop relationships and consult with patrons with disability, further consult with relevant disability sector representatives, conduct audience surveys (see 1.11) | Accessibility Coordinator | Ongoing |
| 6.4 | Maintain contact with Roads and Maritime Services and provide links to their information service regarding accessible public transport options to Sydney Festival venues | Transport Infoline details service were on all venue pages on the 2014 website | Production team to maintain relationship with Roads and Maritime, include their contact information on Domain series / Parramatta opening night pages in the brochure, and continue to include links on all venues pages on website | Production / Marketing | Ongoing, and by 2015 brochure and website deadlines |